## ProjectSchedule
Bathroom Remodelling
|  | Project Start: | 2025-10-21
Nithish Sunkara |  | Today: | 2025-04-14
|  | Display Week: | 1 |  |  | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08
 | time axis 2025-10-20 to 2025-12-14
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-10-20 to 2025-12-14
Planning & Design
Define scope (strip old fixtures, install tile, new fittings) | Nithish | 100% | 2025-10-21 | 2025-10-21 | 1
Identify materials needed (tile, grout, fixtures) | Nithish | 100% | 2025-10-22 | 2025-10-23 | 2
Confirm cousin’s availability (especially for wallpaper & tiling) | Nithish | 100% | 2025-10-24 | 2025-10-24 | 1
Purchase all materials & tools | Nithish | 100% | 2025-10-25 | 2025-10-27 | 3
Finalize design layout | Nithish | 100% | 2025-10-28 | 2025-10-29 | 2
Demolition
Remove vanity, tub, toilet, light fixtures | Nithish | 100% | 2025-10-30 | 2025-11-01 | 3
Wallpaper removal (extra buffer for difficulty) | Nithish & Ram(Cousin) | 100% | 2025-11-02 | 2025-11-05 | 4
Patch upper walls above tile line | Nithish | 100% | 2025-11-06 | 2025-11-07 | 2
Prime walls | Nithish | 100% | 2025-11-08 | 2025-11-08 | 1
Cleanup demo debris | Nithish | 100% | 2025-11-09 | 2025-11-09 | 1
Infrastructure
Plumbing adjustments for new shower & vanity | Nithish | 100% | 2025-11-10 | 2025-11-11 | 2
Electrical adjustments (wiring for new lights, fan, outlets) | Nithish | 100% | 2025-11-12 | 2025-11-13 | 2
Prep wall & floor surfaces for tiling | Nithish | 100% | 2025-11-14 | 2025-11-14 | 1
Confirm tile layout plan | Nithish | 100% | 2025-11-15 | 2025-11-15 | 1
Inspect material availability (tile, grout, sealant) | Nithish | 100% | 2025-11-16 | 2025-11-16 | 1
Installation
Install shower unit | Nithish & Ram(Cousin) | 100% | 2025-11-17 | 2025-11-18 | 2
Floor tile installation | Nithish & Ram(Cousin) | 100% | 2025-11-19 | 2025-11-20 | 2
Wall tile halfway up | Nithish & Ram(Cousin) | 100% | 2025-11-21 | 2025-11-22 | 2
Grouting and sealing | Nithish | 100% | 2025-11-23 | 2025-11-24 | 2
Paint upper walls | Nithish | 100% | 2025-11-25 | 2025-11-25 | 1
Fixtures & Wrap-Up
Install vanity, faucet, light fixtures, mirror | Nithish | 100% | 2025-11-26 | 2025-11-27 | 2
Install new toilet | Nithish | 100% | 2025-11-28 | 2025-11-28 | 1
Final lighting & mirror checks | Nithish | 100% | 2025-11-29 | 2025-11-29 | 1
Final touch-ups (paint, sealant, caulking edges) | Nithish | 100% | 2025-11-30 | 2025-12-01 | 2
Final cleanup & inspection | Nithish & Ram(Cousin) | 100% | 2025-12-02 | 2025-12-03 | 2
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.