## ProjectSchedule
Fundraising event baking cookies
Cookies Baker |  | Project Start: | 2025-05-05
Nithish Sunkara |  | Today: | 2025-05-05
|  | Display Week: | 1 |  |  | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23
 | time axis 2025-05-05 to 2025-06-29
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-05-05 to 2025-06-29
Planning
Create Project Timeline & Strategy | self | 100% | 2025-05-05 | 2025-05-05 | 1
Make shopping list for ingredients & packaging | self | 100% | 2025-05-05 | 2025-05-05 | 1
Check existing baking tools and equipment | self | 100% | 2025-05-05 | 2025-05-05 | 1
Estimate baking time and resources | self | 100% | 2025-05-05 | 2025-05-05 | 1
Draft contingency plans for delays | self | 100% | 2025-05-05 | 2025-05-05 | 1
Procurement
Buy dry ingredients (flour, sugar, etc.) | self | 100% | 2025-05-06 | 2025-05-06 | 1
Buy perishable items (eggs, butter, etc.) | self | 100% | 2025-05-06 | 2025-05-06 | 1
Buy packaging supplies | self | 100% | 2025-05-07 | 2025-05-07 | 1
Transport all items home and organize | self | 100% | 2025-05-07 | 2025-05-07 | 1
Double-check supply completeness | self | 100% | 2025-05-07 | 2025-05-07 | 1
Coordination
Reach to neighbours for oven usage | self | 100% | 2025-05-08 | 2025-05-08 | 1
create oven usage schedule | self | 100% | 2025-05-08 | 2025-05-08 | 1
Share schedule and recipe with neighbours | self | 100% | 2025-05-08 | 2025-05-08 | 1
walk through baking process with neighbours | self | 100% | 2025-05-08 | 2025-05-08 | 1
Confirm all helpers and equipment ready | self | 100% | 2025-05-08 | 2025-05-08 | 1
Baking
Bake Batch 1 (10 dozen) | Neighbour 1 | 100% | 2025-05-09 | 2025-05-09 | 1
Bake Batch 2 (10 dozen) | self | 100% | 2025-05-10 | 2025-05-10 | 1
Bake Batch 3 (10 dozen) | Neighbour 2 | 100% | 2025-05-11 | 2025-05-11 | 1
Quality check and cooling | self | 100% | 2025-05-12 | 2025-05-12 | 1
Store cookies in airtight containers | self | 100% | 2025-05-12 | 2025-05-12 | 1
Packaging & Delivery
Perform taste test for QA | self | 100% | 2025-05-13 | 2025-05-13 | 1
sort cookies for packaging | self | 100% | 2025-05-14 | 2025-05-14 | 1
package cookies in half-dozen sets | self | 100% | 2025-05-14 | 2025-05-14 | 1
label and seal packages Perform taste test for QA | self | 100% | 2025-05-15 | 2025-05-15 | 1
Check packaging & cookie condition | self | 100% | 2025-05-16 | 2025-05-16 | 1
Replace any damaged packaging | self | 100% | 2025-05-17 | 2025-05-17 | 1
Plan transportation logistics for delivery | self | 100% | 2025-05-18 | 2025-05-18 | 1
Final checklist & organize for delivery | self | 100% | 2025-05-19 | 2025-05-24 | 6
Deliver to fundraising site | self | 100% | 2025-05-25 | 2025-05-25 | 1
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.