## ProjectSchedule
Nationwide COVID-19 Vaccine Distribution and Cold Chain Management
|  | Project Start: | 2025-04-15
Nithish Sunkara |  | Today: | 2025-04-14
|  | Display Week: | 1 |  |  | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02
 | time axis 2025-04-14 to 2025-06-08
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-04-14 to 2025-06-08
Planning
Establish federal coordination team | Federal team | 100% | 2025-04-15 | 2025-04-17 | 3
Identify target population zones | Health analytics team | 100% | 2025-04-15 | 2025-04-17 | 3
Engage state/local health departments | State health liaisons | 100% | 2025-04-18 | 2025-04-19 | 2
Draft SOP for ultra-cold logistics | Logistics Specialists | 100% | 2025-04-20 | 2025-04-21 | 2
Create communication plan for public | PR Team | 100% | 2025-04-22 | 2025-04-24 | 3
Procurement
Contract special container suppliers | Procurement Team | 100% | 2025-04-25 | 2025-04-26 | 2
Purchase ultra-cold freezers | Logistics Team | 100% | 2025-04-27 | 2025-04-29 | 3
Procure PPE for medical staff | Medical procurement | 100% | 2025-04-30 | 2025-05-02 | 3
Logistics partner agreements | Legal/logistics team | 100% | 2025-05-03 | 2025-05-06 | 4
Setup inventory tracking system | IT & logistics | 100% | 2025-05-07 | 2025-05-09 | 3
Distribution Preparation
Setup regional storage hubs | Logistics team | 100% | 2025-05-10 | 2025-05-13 | 4
Train personnel on cold chain | Training division | 100% | 2025-05-14 | 2025-05-16 | 3
Conduct dry-runs for logistics | Transport ops | 100% | 2025-05-17 | 2025-05-19 | 3
Map delivery routes | GIS specialists | 100% | 2025-05-20 | 2025-05-21 | 2
Install temperature sensors | Engineering team | 100% | 2025-05-22 | 2025-05-23 | 2
Deployment
Distribute to regional centers | Distribution unit | 100% | 2025-05-24 | 2025-05-27 | 4
Vaccinate frontline workers | Healthcare staff | 100% | 2025-05-28 | 2025-06-01 | 5
Expand to vulnerable groups | Healthcare units | 100% | 2025-06-02 | 2025-06-05 | 4
Cold chain monitoring 24/7 | Cold chain team | 100% | 2025-06-06 | 2025-06-11 | 6
Emergency resupply operations | Contingency ops | 100% | 2025-06-12 | 2025-06-14 | 3
Monitoring & Evaluation
Track vaccine usage & wastage | Analytics team | 100% | 2025-06-15 | 2025-06-17 | 3
Temperature log reviews | QA team | 100% | 2025-06-18 | 2025-06-19 | 2
Collect vaccine impact data | Research unit | 100% | 2025-06-20 | 2025-06-22 | 3
Weekly reports to government | Admin team | 100% | 2025-06-23 | 2025-06-24 | 2
Plan for second dose cycle | Vaccination task force | 100% | 2025-06-26 | 2025-06-27 | 2
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.