## Sheet1
Task Name | Start Date | End Date | Duration (days) | Assigned To | Deliverable | Notes
Project Planning | 05/05/2025 | 05/05/2025 | 1 | Self | Project outline + shopping list | Set up entire plan, list of tools & ingredients
Purchase Ingredients & Supplies | 05/06/2025 | 05/07/2025 | 2 | Self | All materials ready | Buy ingredients, packaging boxes, and labels
Coordinate with Neighbors | 05/08/2025 | 05/08/2025 | 1 | Self | Coordinated oven usage plan | Ask neighbors for help and confirm oven schedule
Bake Batch 1 (5 dozen) | 05/09/2025 | 05/09/2025 | 1 | Neighbor 1 | 5 dozen cookies | Start with first batch using neighbor’s oven
Bake Batch 2 (5 dozen) | 05/10/2025 | 05/10/2025 | 1 | Self | 5 dozen cookies | Use own oven
Bake Batch 3 (5 dozen) | 05/11/2025 | 05/11/2025 | 1 | Neighbor 2 | 5 dozen cookies | Use neighbor’s oven
Bake Batch 4 (5 dozen) | 05/12/2025 | 05/12/2025 | 1 | Self | 5 dozen cookies | Use own oven
Bake Batch 5 (5 dozen) | 05/13/2025 | 05/13/2025 | 1 | Neighbor 1 | 5 dozen cookies | Use neighbor’s oven
Bake Batch 6 (5 dozen) | 05/14/2025 | 05/14/2025 | 1 | Neighbor 2 | 5 dozen cookies | Use neighbor’s oven
Package Cookies (Batch 1–3) | 05/15/2025 | 05/16/2025 | 2 | Self | 30 packages | Package first half of baked cookies
Package Cookies (Batch 4–6) | 05/17/2025 | 05/18/2025 | 2 | Self | 30 packages | Finish packaging
Quality Check | 05/19/2025 | 05/19/2025 | 1 | Self | Approved packages | Taste and inspect packaging
Prepare Delivery | 05/20/2025 | 05/21/2025 | 2 | Self | Delivery logistics ready | Arrange transportation to venue
Final Review & Contingency Check | 05/22/2025 | 05/22/2025 | 1 | Self | Verified logistics | Recheck packaging, transport plan, and contact event team
Buffer / Contingency Day | 05/23/2025 | 05/24/2025 | 2 | Self | Buffer time | Reserved for unexpected delays or rest
Deliver to Event Venue | 05/25/2025 | 05/25/2025 | 1 | Self | Cookies delivered | Deliver on May 25, one day before event